## Slide 1: Marketing Delivery Time Table
© Capacitas Ltd. 2022
Campaign | September | October | November | December | January | February | March
Website Phase 1 (Foundations) | Homepage Design & Content Broken Links (31) Insights Fixes Infographics |  |  |  |  |  | 
Website Phase 2 (Foundations) | Commence content for core service areas (4). Careers Pages Content. | Navigation Content (Core Pages) cont. Speed/Loading All Infographics Careers Pages Design. |  |  |  |  | 
Website Phase 3 (Foundations) |  |  | Content (remaining) SEO Journey Links Design | Content Cloud Masterclass Design | Content On-Going | Content On-Going | Content On-Going
Building An Audience | Social Media Website | PR (Whiteoaks) Social Media Website | PR (Whiteoaks) Social Media Website | PR (Whiteoaks) Social Media Website | Campaigning PR (Whiteoaks) Social Media Website | PR (Whiteoaks) Social Media Website Campaigning | Event PR (Whiteoaks) Social Media Campaigning
Content Building | Cegid Case Study UKHSA Case Study Blog x 1 (TB) Social Media Posts | Jaggaer Guide Vision & Mission Statements Social Media Posts | Jaggaer Guide Generic Capacitas Brochure Social Media Posts | Cloud Masterclass 1 Pagers (sales) PR (Deep Content) Blog x 2 Social Media Posts | Campaign Content Newsletter Event Content 1 pagers (sales) PR & Blog x 2 Social Media | Campaign Content Event Content PR Blog x 2 Social Media | Campaign Content Event Content PR Blog x 2 Social Media
Events |  |  |  |  |  | Masterclass Webinar | Cloud Expo (?) Round Table (Gherkin).

## Slide 2: Marketing Campaign Deliverables
© Capacitas Ltd. 2022
Marcomms Plan 2023/24 | April – June 2023 Q1 | July – Sept Q2 | Oct – Dec Q3 | Jan– March Q4
Content | 5 blogs 1 WP 10 PR articles/News Hijacking | 5 blogs 1WP 10 PR articles/News hijacking | 5 blogs 1WP 10 PR articles/News hijacking | 5 blogs 1 WP 10 PR articles/News hijacking
Campaigns | 1 x Themed Campaign – PE Houses 3 Mailers 1 Generic Campaign (SaaS) 2 Mailers | 1 x Themed Campaign – Public Sector 3 Mailers 1 Generic Campaign 2 Mailers | 1 x Themed Campaign TBC 3 Mailers 1 Generic Campaign 2 Mailers | 1 x Themed Campaign TBC 3 Mailers 1 Generic Campaign 2 Mailers
Webinars | X 1 | X 1 | x 1 | X 1
Events | 1 x round table sponsored by Dynatrace |  | 1 x round table sponsored by Dynatrace | 
Website | Inbound Lead Forms 1 New Infographic 5 Uploaded Blogs 1 Gated WP | Inbound Lead Forms 1 New Infographic 5 Uploaded Blogs 1 Gated WP | Inbound Lead Forms 1 New Infographic 5 Uploaded Blogs 1 Gated WP | Inbound Lead Forms 1 New Infographic 5 Uploaded Blogs 1 Gated WP
Social Media | 16 monthly posts on LinkedIn and FB 130-140 Tweets per month 4 Instagram Posts per month | 16 monthly posts on LinkedIn and FB 130-140 Tweets per month 4 Instagram Posts per month | 16 monthly posts on LinkedIn and FB 130-140 Tweets per month 4 Instagram Posts per month | 16 monthly posts on LinkedIn and FB 130-140 Tweets per month 4 Instagram Posts per month
Newsletter | 1 per quarter | 1 per quarter | 1 per quarter | 1 per quarter

## Slide 3: Marketing Reporting Metrics – Deliverables & Leads
© Capacitas Ltd. 2022
Marcomms Plan 2023/24 | April – June 2023 Q1 | July – Sept Q2 | Oct – Dec Q3 | Jan – March Q4
Content Creation Pyramids of content | 5 blogs (3 delivered by WO’s and 2 by Capacitas team). 1 White Paper Co-Founder or Senior Consultant. 8-10 Pieces of PR Coverage/News Hijacking | 5 blogs (3 delivered by WOs and 2 by Capacitas team). 1White Paper by Co-Founder or Senior Consultant 8-10 Pieces of PR Coverage/News hijacking | 5 blogs (3 delivered by WOs and 2 from Capacitas team). 1White Paper by Co-Founder or Senior Consultant 8-10 Pieces of PR Coverage/News hijacking | 5 blogs (3 delivered by WOs and 2 from Capacitas team). 1White Paper by Co-Founder or Senior Consultant 8-10 Pieces of PR Coverage/News hijacking
Content Quality & Relevance | Number of social media likes, comments and shares. Number of website form submissions Campaign Mailer Opening rate, click through and form submissions. Report results after each campaign | Number of social media likes, comments and shares. Number of website form submissions Campaign Mailer Opening rate, click through and form submissions. Report results after each campaign | Number of social media likes, comments and shares. Number of website form submissions Campaign Mailer Opening rate, click through and form submissions. Report results after each campaign | Number of social media likes, comments and shares. Number of website form submissions Campaign Mailer Opening rate, click through and form submissions. Report results after campaign
Audience Growth | Social Media Followers LI (100) Data Base Increase (50) Events (20) | Social Media Followers (200) Data Base Increase (50) | Social Media Followers (250) Data Base Increase (50) Events (45) | Social Media Followers (250) Data Base Increase (50)
Leads | Prospects Scheduling a Call & Website Form Submissions x 25 Campaigning x 25 Webinar x 15 conversations Events x 20 conversations Cloud Master Class Registrations x 10 95 MQLs 25 Conversations | Prospects Scheduling a Call & Website Form Submissions x 25 Campaigning x 30 Webinar x 15 conversations Cloud Master Class Registrations x 10 80 MQLs 15 Conversations | Prospects Scheduling a Call & Website Form Submissions x 35 Campaigning x 30 Webinar x 25 Events x 20 conversations Cloud Master Class Registrations x 10 120 MQLs 30 Conversations | Prospects Scheduling a Call & Website Form Submission x 35 Campaigning x 30 Webinar x 25 Cloud Master Class x 10 100 MQLs 20 Conversations
Website Traffic | Number of Users Demographics (Who) Source (Where is traffic coming from) Pages per session Average Time on Page Conversion Reporting end of each month | Number of Users Demographics (Who) Source (Where is traffic coming from) Pages per session Average Time on Page Conversion Reporting end of each month | Number of users Demographics (Who) Source (Where is traffic coming from) Pages per session Average Time on Page Conversion Reporting end of each month | Number of Users Demographics (Who) Source (Where) Pages per session Average Time on Page Conversion Reporting end of each month